## Register
PQC Cryptographic Inventory — Register
Deretti Cyber Labs · /quantum/tools/inventory-worksheet · v0.1.0 · CC BY 4.0
System / Service Name | System Owner | Crypto Function | Algorithms in Use | Data Longevity | External Exposure | Trust Role | PQC Vendor Status | Migration Priority | CNSA 2.0 Deadline | Hybrid Supported | Dependencies | Notes / Discovery Method
External API gateway (api.example.com) | Platform Eng | Key establishment | ECDH X25519 + RSA-2048 | >10 yr | Internet-facing | Standard | Roadmap | P1 | Jan 2027 preferred | Unknown | Front-door for all customer traffic; load balancer chain | openssl s_client probe 2026-05
Internal root CA (PKI) | Security Eng | Signature | RSA-4096 | >10 yr | Internal only | CA / Root trust | Unknown | P1 | 2031 required | No | Signs every internal cert; replacement cascades | Identified during PKI annual review
Code-signing service | DevSecOps | Signature | ECDSA P-256 | 5–10 yr | Internal only | Signing pipeline | Roadmap | P1 | 2031 required | No | Signs all production binaries; OS-level trust anchors | Vendor query Q2 2026
Site-to-site VPN (HQ ↔ datacenter) | Network Ops | Key establishment | IKEv2 / DH-MODP-2048 | 5–10 yr | Partner | Standard | Roadmap | P2 | Jan 2027 preferred | Unknown | Connects HQ to colocated infra; depends on appliance fw | Vendor PSIRT advisory pending
Customer-facing TLS termination (CDN) | Platform Eng | Key establishment | ECDH P-256 | 1–5 yr | Internet-facing | Standard | Available now | P2 | Jan 2026 available | Yes | CDN provider supports hybrid ML-KEM as opt-in | Provider release notes 2026-04
OAuth identity provider (IdP) | Identity Eng | Signature | RS256 (RSA-2048) | 5–10 yr | Internet-facing | Standard | Roadmap | P1 | 2031 required | No | Issues JWTs for all federated apps; rotation required | Confirmed via JWKS endpoint
Backup encryption (cold archive) | Storage | Symmetric | AES-256-GCM | >10 yr | Internal only | Standard | Not applicable | P3 | Not applicable | N/A | Symmetric; key uplift sufficient; key wrap is the concern | Annual storage audit 2026
Firmware update channel (IoT fleet) | Embedded | Signature | ECDSA P-256 | >10 yr | Internet-facing | Signing pipeline | Unknown | P1 | 2031 required | No | Device fleet has 7–10 yr field life; firmware OTA | Vendor RFP issued 2026-Q1
SSH bastion (admin access) | Security Eng | Key establishment | ECDH curve25519-sha256 | <1 yr | Internet-facing | Standard | Roadmap | P2 | Jan 2027 preferred | Unknown | Session ephemeral; HNDL window is short | OpenSSH 9.x upgrade scheduled
Internal SaaS — HR records | IT | Key establishment | TLS 1.2 (mixed RSA/ECDH) | 5–10 yr | Partner | Standard | Unknown | P2 | Jan 2027 preferred | Unknown | Vendor-hosted SaaS; coverage depends on provider | Open vendor query Q3 2026

## Priority Scoring
Priority Scoring — Three-axis derivation
Longevity + External Exposure + Trust Role → Migration Priority
Data Longevity | External Exposure | Trust Role | Priority | Why
>5 yr | Internet-facing | High trust (CA / VPN / signing) | P1 | Long-lived + external + high-trust → HNDL exposed + cascade impact.
>5 yr | Internet-facing | Standard | P1 | Long-lived + external → HNDL exposed today.
>5 yr | Partner | High trust | P1 | Long-lived + partner-visible + cascade impact.
>5 yr | Internal only | High trust | P1 – P2 | Long-lived high-trust internal — depends on insider-risk posture.
1–5 yr | Internet-facing | Standard | P2 | Externally visible but data does not outlast CNSA 2.0 inflection.
1–5 yr | Partner | Standard | P2 | Partner-visible but bounded confidentiality window.
<1 yr | Internet-facing | Standard | P2 | External but very short-lived. Treat as P2.
1–5 yr | Internal only | Standard | P3 | Internal-only and short-lived → low HNDL exposure.
<1 yr | Internal only | Standard | P3 | Internal-only and ephemeral → P3.

## Companion Guide
Companion Guide — How to use this worksheet
Deretti Cyber Labs · /quantum/tools/inventory-worksheet · v0.1.0 · CC BY 4.0
1 · Why inventory first | Discovery is the first real control. Without a current register, no priority ranking is possible — and any vendor proposal that promises to 'solve' the problem before you've inventoried it should be treated skeptically. Most mid-market organizations end up with about 40 rows total: 5–15 in P1, the rest in P2 or P3.
2 · How to discover | Run four passes and cross-reference: (a) Network probe — openssl s_client on exposed endpoints, internal cert inventories, egress allow-list audits. (b) Code and config scan — grep for RSA, ECDH, ECDSA, X25519, secp256r1 across repositories, Helm charts, Terraform, Ansible. (c) Vendor query — standard letter or RFP question. (d) Cloud-provider audit — AWS KMS, Azure Key Vault, GCP Cloud KMS each have PQC support that varies by service and region.
3 · Filling each row | Each row is one cryptographic dependency. Use the dropdowns where provided; free-text fields are for context. The Migration Priority is derived (see Priority Scoring sheet) — fill it last, after Longevity, Exposure, and Trust Role are confirmed.
4 · Priority derivation | See the Priority Scoring sheet. Longevity > 5 yr is the dominant signal — long-lived data is HNDL-exposed today regardless of where it sits. Internet-facing pushes priority up. High-trust roles (CA, root, signing pipelines) push priority up further because they cascade.
5 · Review cadence | Quarterly: PQC Vendor Status column (vendor roadmaps move on quarterly cycles). Annually: full register pass (ownership, longevity, trust). Triggered: vendor PQC GA announcement, CISA category list update, major library version change.
6 · Evidence and audit trail | Use the Notes / Discovery Method column as the audit trail — which tool surfaced the row, who confirmed it, when. The register is the citation source for any future PQC audit defense; treat it accordingly.
7 · Cross-references | Web reference: https://deretticyberlabs.com/quantum/tools/inventory-worksheet.html · Vendor RFP Rubric (next tool): https://deretticyberlabs.com/quantum/tools/vendor-rfp-rubric.html · IT Technicians briefing: https://deretticyberlabs.com/quantum/briefings/it-technicians.html · Active Research note: https://deretticyberlabs.com/research/active/post-quantum-cryptographic-exposure.html